## Sheet1
Budgeting App Project Management
| TASK NAME | START DATE | END DATE | DURATION (WORK DAYS) | PERCENT COMPLETE | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12 |  |  |  |  | WEEK 13 |  |  |  |  | WEEK 14 |  |  |  |  | WEEK 14
[6 empty] | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F
First Sample Project | bar: WEEK 1 M to WEEK 2 M
| Research | 2019-02-11 | 2019-02-15 | 5 | 100% | bar: WEEK 1 M to WEEK 2 M
| Literature Reivew | 2019-02-18 | 2019-02-22 | 5 | 100%
| Participant Surveys | 2019-03-18 | 2019-03-29 | 10 | 0% | bar: WEEK 1 M to WEEK 2 M; WEEK 4 M to WEEK 5 F
| Coding the Application | 2019-03-25 | 2019-04-05 | 10 | 0% | bar: WEEK 1 M to WEEK 2 M; WEEK 5 M to WEEK 6 F
| Participants Use Application | 2019-04-08 | 2019-04-19 | 10 | 0% | bar: WEEK 1 M to WEEK 2 M; WEEK 7 M to WEEK 9 F
| Site/Application Maintenance | 2019-04-08 | 2019-04-19 | 10 | 0% | bar: WEEK 1 M to WEEK 2 M; WEEK 7 M to WEEK 9 F
| Reporting and Presentation | 2019-04-22 | 2019-04-26 | 5 | 0% | bar: WEEK 1 M to WEEK 2 M
Formulas:
DURATION (WORK DAYS) = NETWORKDAYS([START DATE],[END DATE])